## Sheet1
Iteration | Story | Tasks | Estimated Hours | Actual Hours | Assigned Member | isCompleted | dateCompleted | Notes
Planning | Meeting Log
|  | Create initial log | 1 | 1 | Pete | Yes | 2013-09-26
|  | Update as Necessary | 10 | 8 | Pete | Yes
Planning | Weekly Reports
|  | Create and share weekly reports | 10 | 12 | Pete | Yes | 2013-10-07
Planning | Research of Languages
|  | Research HTML and Javascript | 2 | 2 | Ari & Jeremiah | Yes | 2013-10-10
|  | Implement Javascript open XML and get values | 5 | 8 | Ari & Jeremiah | Yes | 2013-10-15
|  | Style Javascript output of XML for readability | 2 | 1 | Ari & Jeremiah | Yes | 2013-10-15
Planning | Documentation
|  | Create SRS template and share to members | 2 | 3 | Kevin | Yes | 2013-10-16
|  | Assign sections to necessary members | 1 | 1 | Kevin | Yes | 2013-10-16
|  | Fill out assigned section | 12 | 15 | Kevin, Pete, Jeremiah, Ari | Yes | 2013-10-30
|  | Create Vision doc template and share with team | 2 | 2 | Kevin | Yes | 2013-10-16
|  | Update Vision doc | 2 | 4 | Kevin, Pete | Yes | 2013-10-24
Planning | Contact Customer
|  | Schedule Meeting | 1 | 1 | Jeremiah | Yes | 2013-09-24
|  | Notify and introduce team | 0.5 | 0.5 | Jeremiah | Yes | 2013-09-24
|  | Reserve Room | 0.5 | 0.5 | Jeremiah | Yes | 2013-09-24
|  | Setup information transfer from team to client | 0.5 | 0.5 | Jeremiah | Yes | 2013-09-26
Planning | Setup Tools
|  | Establish set of tools to be used | 2 | 1 | Jeremiah | Yes | 2013-10-15 | Chose to use Github for code sharing, Google Drive for documentation, Koding for development, and scrumDo for scrum management
|  | Setup Github | 1 | 4 | Kevin, Pete, Jeremiah, Ari | Yes | 2013-10-15 | Allows for nice version control and sharing between developers
|  | Setup Google Drive folder | 0.5 | 1 | Kevin, Pete, Jeremiah, Ari | Yes | 2013-10-15 | Great sharing, multiple editors, privacy, and rights control
|  | Setup and evaluate Koding | 2 | 3 | Jeremiah, Ari | Yes | 2013-10-15 | Cloud platform which allows for development from anywhere. We stopped using this because it was brought to our attention that the client does not want to run a webserver
|  | Setup scrumDo | 2 | 2 | Jeremiah | Yes | 2013-10-15 | This was a nice scrum tool that allowed for Google incorporation and had an iPhone app. However it lacked features Burgandy wanted so we switched to Rally.
|  | Change to Rally | 4 | 6 | Pete | Yes | 2013-10-20
Dates: 9/13 - 10/20 | Totals for this Iteration |  | 63 | 76.5
Design | Influence Meeting
|  | Meeting Arrangements | 1 | 1 | Pete | Yes | 2013-11-12
|  | Notify Team | 0.5 | 0.5 | Pete | Yes | 2013-11-12
|  | Create Reservation | 0.5 | 0.5 | Jeremiah | Yes | 2013-11-12
|  | Material Organization | 2 | 2 | Pete | Yes | 2013-11-19
|  | Create Lists of Questions | 4 | 4 | Kevin, Pete, Jeremiah, Ari | Yes | 2013-11-19
|  | Document What was learned | 1 | 1 | Kevin, Pete, Jeremiah, Ari | Yes | 2013-11-19 | Typically government applications are very slow, Liked our tab idea
Design | Use Case Document
|  | Define Use Cases | 2 | 2 | Pete, Jeremiah | Yes | 2013-11-15
|  | Create Use Case diagrams | 3 | 3 | Pete, Jeremiah | Yes | 2013-11-15
Design | Interface Design
|  | Create Interface Templates | 4 | 4 | Kevin, Pete, Jeremiah, Ari | Yes | 2013-11-23
Design | Update Documentation
|  | Update SRS to represent changes | 6 | 5 | Kevin, Pete, Jeremiah, Ari | Yes | 2013-11-24
|  | Software Development Plan | 10 | 10 | Kevin, Pete, Jeremiah, Ari | Yes | 2013-11-24
Design | Construct Test Docs
|  | Create example RTM | 6 | 6 | Jeremiah, Ari | Yes | 2013-11-10
|  | Research xml and schemas | 4 | 4 | Kevin, Pete | Yes | 2013-11-04
|  | Create test xml's so coding can start | 10 | 10 | Kevin, Pete, Jeremiah, Ari | Yes | 2013-11-01
Dates: 10/21 - 11/27 | Totals for this Iteration |  | 54 | 53
Creation | Display XML to User
|  | Output XML nodeNames into table of contents | 2 | 4 | Ari | Yes | 2014-02-20
|  | Output XML nodeValues into preview pane | 2 | 8 | Ari | Yes | 2014-02-26 | This was a huge challenge in Javascript and took an unnecessary amount of time to create and also to process the output. Linking between the TOC element and what was displayed also was a challenge. This was first done by loading the XML into a cookie. This caused problems with Sections overwriting each other. Sessvars solved this but the time complexity was still unnacceptable. This was solved by using the XSLT output as part of our user interface
|  | Display tabs for access to other documents in project | 1 | 1 | Ari | Yes | 2014-04-07
|  | Change displayed output to XSLT result | 4 | 6 | Jeremiah | Yes | 2014-03-30 | Once XSLT was completed its output is used not only for the GUI but also for the downloadable output.
Creation | Make XML editable
|  | Put preview into textarea | 1 | 1 | Ari | Yes | 2014-02-26
|  | Implement save method for each XML element | 25 | 50 | Jeremiah, Ari | Yes | 2014-04-01 | Originally this was written to completely re-write the XML. This was because we struggled to find a way to edit an individual node. This method never completely wrote the xml correctly as it would close tags before all its children were written. With these problems we also knew version control would be a struggle. XSLT eventually solved these problems
|  | Implementation of isNewest tags | 1 | 1 | Jeremiah | Yes | 2014-04-03
|  | Changes for XSLT | 4 | 8 | Jeremiah | Yes | 2014-03-31 | Since XSLT easily broke Para's into divs and used direct XML values instead of sessvars appending children or nodes with XML doesn't need to be re-written to make changes.
Creation | Create XML Schema's
|  | Implement Schema for SRS, Use case, and Test case | 6 | 10 | Pete, Kevin | Yes | 2014-03-14
|  | Implement Project schema | 1 | 3 | Pete, Kevin, Jeremiah | Yes | 2014-03-14
|  | Review with client | 4 | 6 | Kevin | Yes | 2014-03-14
Creation | Create XML's that follow schema
|  | Revise all XML's to assure they meet schema requirements | 4 | 4 | Pete, Kevin | Yes | 2014-03-16
Creation | Create XSL
|  | Create XSL stylesheet for all XML's so they can be displayed to the User | 8 | 12 | Pete, Kevin, Jeremiah | Yes | 2014-04-03
|  | Edit XSL to include edit option | 2 | 4 | Jeremiah | Yes | 2014-04-06 | Document command was not supported by javascript, this was fixed with setAttribute command
Creation | Make references between documents
|  | Edit schema to allow linking between XML's within a project | 2 | 2 | Kevin | Yes | 2014-03-27
|  | Edit XSL to show links to User | 4 | 4 | Jeremiah | Yes | 2014-04-06
Creation | Make RTM
|  | Make XSL to show RTM | 2 |  |  | No
Creation | Downloadable HTML output
|  | Make button to download HTML for uneditable viewing | 1 | 1 | Jeremiah | Yes | 2014-04-06
Dates: 11/28 - 3/14 | Totals for this Iteration |  | 74 | 125
Testing | Determine Completeness of System
|  | Ensure all requirements of project are met | 12 |  | Peter, Kevin | No
|  | Make necessary changes | 12 |  | Jeremiah, Ari | No
Testing | Use Case Documentation
|  | Ensure all Use Cases are met | 6 |  | Peter, Kevin | No
|  | Make Use Case document of what occured using our system | 4 |  | Peter | No
Testing | Test Case Documentation
|  | Make Test Case document of what occured using our system | 4 |  | Kevin | No
Dates: 3/15 - 5/01 | Totals for this Iteration |  | 38 | 0
END
Planning |  | Tasks | Estimated Hours | Actual Hours |  | is Completed
|  |  | 1 | 1 |  | Yes
|  | Update as Necessary | 10 | 8 |  | Yes
|  | Research HTML and Javascript | 2 | 2 |  | Yes
|  | Implement XML open and get values | 5 | 8 |  | Yes
|  | Style Javascript output of XML for readability | 2 | 1 |  | Yes
|  | Create SRS template and share to members | 2 | 3 |  | Yes
|  | Assign sections to necessary members | 1 | 1 |  | Yes
|  | Fill out assigned section | 12 | 15 |  | Yes
|  | Create Vision doc template and share with team | 2 | 2 |  | Yes
|  | Update Vision doc | 2 | 4 |  | Yes
|  | Schedule Meeting | 1 | 1 |  | Yes
|  | Notify and introduce team | 0.5 | 0.5 |  | Yes
|  | Reserve Room | 0.5 | 0.5 |  | Yes
|  | Setup information transfer from team to client | 0.5 | 0.5 |  | Yes
|  | Establish set of tools to be used | 2 | 1 |  | Yes
|  | Setup Github | 1 | 4 |  | Yes
|  | Setup Google Drive folder | 0.5 | 1 |  | Yes
|  | Setup and evaluate Koding | 2 | 3 |  | Yes
|  | Setup scrumDo | 2 | 2 |  | Yes
|  | Change to Rally | 4 | 6 |  | Yes
Extra Time | 0.1782945736 |  | Estimated Hours | 53
Estimated Time | 0.8217054264 |  | Actual Hours | 64.5
Design |  | Tasks | Estimated Hours | Actual Hours |  | is Completed
|  | Create and share weekly reports | 10 | 12 |  | Yes
|  | Meeting Arrangements | 1 | 1 |  | Yes
|  | Notify Team | 0.5 | 0.5 |  | Yes
|  | Create Reservation | 0.5 | 0.5 |  | Yes
|  | Material Organization | 2 | 2 |  | Yes
|  | Create Lists of Questions | 4 | 4 |  | Yes
|  | Document What was learned | 1 | 1 |  | Yes
|  | Define Use Cases | 2 | 2 |  | Yes
|  | Create Use Case diagrams | 3 | 3 |  | Yes
|  | Create Interface Templates | 4 | 4 |  | Yes
|  | Update SRS to represent changes | 6 | 5 |  | Yes
|  | Software Development Plan | 10 | 10 |  | Yes
|  | Create example RTM | 6 | 6 |  | Yes
|  | Research xml and schemas | 4 | 4 |  | Yes
|  | Create test xml's so coding can start | 10 | 10 |  | Yes
Extra Time | 0.01538461538 |  | Estimated Hours | 64
Estimated Time | 0.9846153846 |  | Actual Hours | 65
Creation |  | Tasks | Estimated Hours | Actual Hours |  | is Completed
|  | Output XML nodeNames into table of contents | 2 | 4 |  | Yes
|  | Output XML nodeValues into preview pane | 2 | 8 |  | Yes
|  | Display tabs for access to other documents in project | 1 | 1 |  | Yes
|  | Change displayed output to XSLT result | 4 | 6 |  | Yes
|  | Put preview into textarea | 1 | 1 |  | Yes
|  | Implement save method | 4 | 10 |  | Yes
|  | Implementation of isNewest tags | 1 | 1 |  | Yes
|  | Changes for XSLT | 4 | 8 |  | Yes
|  | Implement Schema for SRS, Use case, and Test case | 6 | 10 |  | Yes
|  | Implement Project schema | 1 | 3 |  | Yes
|  | Review with client | 4 | 6 |  | Yes
|  | Revise all XML's to assure they meet schema requirements | 4 | 4 |  | Yes
|  | Create XSL stylesheet for all XML's so they can be displayed to the User | 8 | 12 |  | Yes
|  | Edit XSL to include edit option | 2 | 4 |  | Yes
|  | Edit schema to allow linking between XML's within a project | 2 | 2 |  | Yes
|  | Edit XSL to show links to User | 4 | 4 |  | Yes
|  | Make XSL to show RTM | 2 | 0 |  | No
|  | Make button to download HTML for uneditable viewing | 1 | 1 |  | Yes
Extra Time | 0.3764705882 |  | Estimated Hours | 53
Estimated Time | 0.6235294118 |  | Actual Hours | 85
Testing | Determine Completeness of System
|  | Ensure all requirements of project are met | 12 |  | Peter, Kevin | No
|  | Make necessary changes | 12 |  | Jeremiah, Ari | No
Testing | Use Case Documentation
|  | Ensure all Use Cases are met | 6 |  | Peter, Kevin | No
|  | Make Use Case document of what occured using our system | 4 |  | Peter | No
Testing | Test Case Documentation
|  | Make Test Case document of what occured using our system | 4 |  | Kevin | No
Dates: 3/15 - 5/01 | Totals for this Iteration |  | 38 | 0
|  |  |  | Estimated | Actual Hours
|  |  | Planning Iteration | 63 | 76.5
|  |  | Design Iteration | 54 | 53
|  |  | Creation Iteration | 100 | 156
|  |  | Total Estimate Hours | 170
|  |  | Total Actual Hours | 214.5

## Sheet2
| Date | Actual | Estimated
1 | 2013-09-26 | 62 | 63 | 63
0.5 | 2013-09-24 | 61.5 | 60
0.5 | 2013-09-24 | 61 | 57
0.5 | 2013-09-26 | 60.5 | 54
0.5 | 2013-10-15 | 60 | 51
1 | 2013-10-16 | 59 | 48
1 | 2013-09-24 | 58 | 45
1 | 2013-10-15 | 57 | 42
2 | 2013-10-10 | 55 | 39
2 | 2013-10-15 | 53 | 36
2 | 2013-10-16 | 51 | 33
2 | 2013-10-16 | 49 | 30
2 | 2013-10-24 | 47 | 27
2 | 2013-10-15 | 45 | 24
2 | 2013-10-15 | 43 | 21
2 | 2013-10-15 | 41 | 18
4 | 2013-10-20 | 37 | 15
5 | 2013-10-15 | 32 | 12
10 | 2013-10-09 | 22 | 9
10 | 2013-10-07 | 12 | 6
12 | 2013-10-30 | 0.5 | 3
| 2013-11-01 | 0 | 0
63

## Sheet3
Date | Actual | Estimate
2014-02-20 | 53 | 53 | 2
2014-02-26 | 51 | 49.88235294 | 2 | 3.117647059
2014-02-26 | 49 | 46.76470588 | 1
2014-03-14 | 48 | 43.64705882 | 6
2014-03-14 | 42 | 40.52941176 | 1
2014-03-14 | 41 | 37.41176471 | 4
2014-03-16 | 37 | 34.29411765 | 4
2014-03-27 | 33 | 31.17647059 | 2
2014-03-30 | 31 | 28.05882353 | 4
2014-03-31 | 27 | 24.94117647 | 4
2014-04-01 | 23 | 21.82352941 | 4
2014-04-03 | 19 | 18.70588235 | 1
2014-04-03 | 18 | 15.58823529 | 8
2014-04-06 | 10 | 12.47058824 | 2
2014-04-06 | 8 | 9.352941176 | 4
2014-04-06 | 4 | 6.235294118 | 1
2014-04-07 | 0 | 3.117647059 | 1
0
2
53

## Sheet4
Iteration | Story | Tasks | Estimated Hours | Actual Hours | Assigned Member | isCompleted | dateCompleted | Notes
|  | Output XML nodeNames into table of contents | 2 | 4 | Ari | Yes | 2014-02-20
|  | Output XML nodeValues into preview pane | 2 | 8 | Ari | Yes | 2014-02-26 | This was a huge challenge in Javascript and took an unnecessary amount of time to create and also to process the output. Linking between the TOC element and what was displayed also was a challenge. This was first done by loading the XML into a cookie. This caused problems with Sections overwriting each other. Sessvars solved this but the time complexity was still unnacceptable. This was solved by using the XSLT output as part of our user interface
|  | Display tabs for access to other documents in project | 1 | 1 | Ari | Yes | 2014-04-07
|  | Put preview into textarea | 1 | 1 | Ari | Yes | 2014-02-26
|  | Research HTML and Javascript | 2 | 2 | Ari
|  | Implement Javascript open XML and get values | 5 | 8 | Ari
|  | Style Javascript output of XML for readability | 2 | 1 | Ari
|  | Setup and evaluate Koding | 2 | 3 | Ari
|  | Create example RTM | 6 | 6 | Ari
|  | Implement save method for each XML element | 25 | 50 | Ari
|  | Make necessary changes | 12 | 20 | Ari
|  | Fill out assigned section | 12 | 15 | Group | Yes | 2013-10-30
|  | Setup Github | 1 | 4 | Group | Yes | 2013-10-15 | Allows for nice version control and sharing between developers
|  | Setup Google Drive folder | 0.5 | 1 | Group | Yes | 2013-10-15 | Great sharing, multiple editors, privacy, and rights control
|  | Create Lists of Questions | 4 | 4 | Group | Yes | 2013-11-19
|  | Document What was learned | 1 | 1 | Group | Yes | 2013-11-19 | Typically government applications are very slow, Liked our tab idea
|  | Create Interface Templates | 4 | 4 | Group | Yes | 2013-11-23
|  | Update SRS to represent changes | 6 | 5 | Group | Yes | 2013-11-24
|  | Software Development Plan | 10 | 10 | Group | Yes | 2013-11-24
|  | Create test xml's so coding can start | 10 | 10 | Group | Yes | 2013-11-01
|  | Implement Project schema | 1 | 3 | Group | Yes | 2014-03-14
|  | Create XSL stylesheet for all XML's so they can be displayed to the User | 8 | 12 | Group | Yes | 2014-04-03
|  | Define Use Cases | 2 | 2 | Jeremiah
|  | Create Use Case diagrams | 3 | 3 | Jeremiah
|  | Research HTML and Javascript | 2 | 2 | Jeremiah | Yes | 2013-10-10
|  | Implement Javascript open XML and get values | 5 | 8 | Jeremiah | Yes | 2013-10-15
|  | Style Javascript output of XML for readability | 2 | 1 | Jeremiah | Yes | 2013-10-15
|  | Schedule Meeting | 1 | 1 | Jeremiah | Yes | 2013-09-24
|  | Notify and introduce team | 0.5 | 0.5 | Jeremiah | Yes | 2013-09-24
|  | Reserve Room | 0.5 | 0.5 | Jeremiah | Yes | 2013-09-24
|  | Setup information transfer from team to client | 0.5 | 0.5 | Jeremiah | Yes | 2013-09-26
|  | Establish set of tools to be used | 2 | 1 | Jeremiah | Yes | 2013-10-15 | Chose to use Github for code sharing, Google Drive for documentation, Koding for development, and scrumDo for scrum management
|  | Setup scrumDo | 2 | 2 | Jeremiah | Yes | 2013-10-15 | This was a nice scrum tool that allowed for Google incorporation and had an iPhone app. However it lacked features Burgandy wanted so we switched to Rally.
|  | Create Reservation | 0.5 | 0.5 | Jeremiah | Yes | 2013-11-12
|  | Change displayed output to XSLT result | 4 | 6 | Jeremiah | Yes | 2014-03-30 | Once XSLT was completed its output is used not only for the GUI but also for the downloadable output.
|  | Implementation of isNewest tags | 1 | 1 | Jeremiah | Yes | 2014-04-03
|  | Changes for XSLT | 4 | 8 | Jeremiah | Yes | 2014-03-31 | Since XSLT easily broke Para's into divs and used direct XML values instead of sessvars appending children or nodes with XML doesn't need to be re-written to make changes.
|  | Edit XSL to include edit option | 2 | 4 | Jeremiah | Yes | 2014-04-06 | Document command was not supported by javascript, this was fixed with setAttribute command
|  | Edit XSL to show links to User | 4 | 4 | Jeremiah | Yes | 2014-04-06
|  | Make button to download HTML for uneditable viewing | 1 | 1 | Jeremiah | Yes | 2014-04-06
|  | Setup and evaluate Koding | 2 | 3 | Jeremiah | Yes | 2013-10-15 | Cloud platform which allows for development from anywhere. We stopped using this because it was brought to our attention that the client does not want to run a webserver
|  | Create example RTM | 6 | 6 | Jeremiah | Yes | 2013-11-10
|  | Implement save method for each XML element | 25 | 50 | Jeremiah | Yes | 2014-04-01 | Originally this was written to completely re-write the XML. This was because we struggled to find a way to edit an individual node. This method never completely wrote the xml correctly as it would close tags before all its children were written. With these problems we also knew version control would be a struggle. XSLT eventually solved these problems
|  | Make necessary changes | 12 |  | Jeremiah | No
|  | Create SRS template and share to members | 2 | 3 | Kevin | Yes | 2013-10-16
|  | Assign sections to necessary members | 1 | 1 | Kevin | Yes | 2013-10-16
|  | Create Vision doc template and share with team | 2 | 2 | Kevin | Yes | 2013-10-16
|  | Review with client | 4 | 6 | Kevin | Yes | 2014-03-14
|  | Edit schema to allow linking between XML's within a project | 2 | 2 | Kevin | Yes | 2014-03-27
|  | Make Test Case document of what occured using our system | 4 |  | Kevin | No
|  | Implement Schema for SRS, Use case, and Test case | 6 | 10 | Kevin
|  | Revise all XML's to assure they meet schema requirements | 4 | 4 | Kevin
|  | Ensure all requirements of project are met | 12 |  | Kevin
|  | Ensure all Use Cases are met | 6 |  | Kevin
|  | Update Vision doc | 2 | 4 | Kevin
|  | Research xml and schemas | 4 | 4 | Kevin
|  | Update Vision doc | 2 | 4 | Pete | Yes | 2013-10-24
|  | Research xml and schemas | 4 | 4 | Pete | Yes | 2013-11-04
|  | Create initial log | 1 | 1 | Pete | Yes | 2013-09-26
|  | Update as Necessary | 10 | 8 | Pete | Yes
|  | Create and share weekly reports | 10 | 12 | Pete | Yes | 2013-10-07
|  | Change to Rally | 4 | 6 | Pete | Yes | 2013-10-20
|  | Meeting Arrangements | 1 | 1 | Pete | Yes | 2013-11-12
|  | Notify Team | 0.5 | 0.5 | Pete | Yes | 2013-11-12
|  | Material Organization | 2 | 2 | Pete | Yes | 2013-11-19
|  | Define Use Cases | 2 | 2 | Pete | Yes | 2013-11-15
|  | Create Use Case diagrams | 3 | 3 | Pete | Yes | 2013-11-15
|  | Implement Schema for SRS, Use case, and Test case | 6 | 10 | Pete | Yes | 2014-03-14
|  | Revise all XML's to assure they meet schema requirements | 4 | 4 | Pete | Yes | 2014-03-16
|  | Ensure all requirements of project are met | 12 |  | Pete | No
|  | Ensure all Use Cases are met | 6 |  | Pete | No
|  | Make Use Case document of what occured using our system | 4 |  | Peter | No
Planning | Meeting Log
Planning | Weekly Reports
Planning | Research of Languages
Planning | Documentation
Planning | Contact Customer
Planning | Setup Tools
Dates: 9/13 - 10/20 | Totals for this Iteration |  | 118.5 | 90.5
Design | Influence Meeting
Design | Use Case Document
Design | Interface Design
Design | Update Documentation
Design | Construct Test Docs
Dates: 10/21 - 11/27 | Totals for this Iteration |  | 163 | 119
Creation | Display XML to User
Creation | Make XML editable
Creation | Create XML Schema's
Creation | Create XML's that follow schema
Creation | Create XSL
Creation | Make references between documents
Creation | Make RTM
|  | Make XSL to show RTM | 2 |  |  | No
Creation | Downloadable HTML output
Dates: 11/28 - 3/14 | Totals for this Iteration |  | 283.5 | 209.5
Testing | Determine Completeness of System
Testing | Use Case Documentation
Testing | Test Case Documentation
Dates: 3/15 - 5/01 | Totals for this Iteration |  | 283.5 | 209.5
END
Planning |  | Tasks | Estimated Hours | Actual Hours |  | is Completed
|  |  | 1 | 1 |  | Yes
|  | Update as Necessary | 10 | 8 |  | Yes
|  | Research HTML and Javascript | 2 | 2 |  | Yes
|  | Implement XML open and get values | 5 | 8 |  | Yes
|  | Style Javascript output of XML for readability | 2 | 1 |  | Yes
|  | Create SRS template and share to members | 2 | 3 |  | Yes
|  | Assign sections to necessary members | 1 | 1 |  | Yes
|  | Fill out assigned section | 12 | 15 |  | Yes
|  | Create Vision doc template and share with team | 2 | 2 |  | Yes
|  | Update Vision doc | 2 | 4 |  | Yes
|  | Schedule Meeting | 1 | 1 |  | Yes
|  | Notify and introduce team | 0.5 | 0.5 |  | Yes
|  | Reserve Room | 0.5 | 0.5 |  | Yes
|  | Setup information transfer from team to client | 0.5 | 0.5 |  | Yes
|  | Establish set of tools to be used | 2 | 1 |  | Yes
|  | Setup Github | 1 | 4 |  | Yes
|  | Setup Google Drive folder | 0.5 | 1 |  | Yes
|  | Setup and evaluate Koding | 2 | 3 |  | Yes
|  | Setup scrumDo | 2 | 2 |  | Yes
|  | Change to Rally | 4 | 6 |  | Yes
Extra Time | 0.1782945736 |  | Estimated Hours | 53
Estimated Time | 0.8217054264 |  | Actual Hours | 64.5
Design |  | Tasks | Estimated Hours | Actual Hours |  | is Completed
|  | Create and share weekly reports | 10 | 12 |  | Yes
|  | Meeting Arrangements | 1 | 1 |  | Yes
|  | Notify Team | 0.5 | 0.5 |  | Yes
|  | Create Reservation | 0.5 | 0.5 |  | Yes
|  | Material Organization | 2 | 2 |  | Yes
|  | Create Lists of Questions | 4 | 4 |  | Yes
|  | Document What was learned | 1 | 1 |  | Yes
|  | Define Use Cases | 2 | 2 |  | Yes
|  | Create Use Case diagrams | 3 | 3 |  | Yes
|  | Create Interface Templates | 4 | 4 |  | Yes
|  | Update SRS to represent changes | 6 | 5 |  | Yes
|  | Software Development Plan | 10 | 10 |  | Yes
|  | Create example RTM | 6 | 6 |  | Yes
|  | Research xml and schemas | 4 | 4 |  | Yes
|  | Create test xml's so coding can start | 10 | 10 |  | Yes
Extra Time | 0.01538461538 |  | Estimated Hours | 64
Estimated Time | 0.9846153846 |  | Actual Hours | 65
Creation |  | Tasks | Estimated Hours | Actual Hours |  | is Completed
|  | Output XML nodeNames into table of contents | 2 | 4 |  | Yes
|  | Output XML nodeValues into preview pane | 2 | 8 |  | Yes
|  | Display tabs for access to other documents in project | 1 | 1 |  | Yes
|  | Change displayed output to XSLT result | 4 | 6 |  | Yes
|  | Put preview into textarea | 1 | 1 |  | Yes
|  | Implement save method | 4 | 10 |  | Yes
|  | Implementation of isNewest tags | 1 | 1 |  | Yes
|  | Changes for XSLT | 4 | 8 |  | Yes
|  | Implement Schema for SRS, Use case, and Test case | 6 | 10 |  | Yes
|  | Implement Project schema | 1 | 3 |  | Yes
|  | Review with client | 4 | 6 |  | Yes
|  | Revise all XML's to assure they meet schema requirements | 4 | 4 |  | Yes
|  | Create XSL stylesheet for all XML's so they can be displayed to the User | 8 | 12 |  | Yes
|  | Edit XSL to include edit option | 2 | 4 |  | Yes
|  | Edit schema to allow linking between XML's within a project | 2 | 2 |  | Yes
|  | Edit XSL to show links to User | 4 | 4 |  | Yes
|  | Make XSL to show RTM | 2 | 0 |  | No
|  | Make button to download HTML for uneditable viewing | 1 | 1 |  | Yes
Extra Time | 0.3764705882 |  | Estimated Hours | 53
Estimated Time | 0.6235294118 |  | Actual Hours | 85
Testing | Determine Completeness of System
|  | Ensure all requirements of project are met | 12 |  | Peter, Kevin | No
|  | Make necessary changes | 12 |  | Jeremiah, Ari | No
Testing | Use Case Documentation
|  | Ensure all Use Cases are met | 6 |  | Peter, Kevin | No
|  | Make Use Case document of what occured using our system | 4 |  | Peter | No
Testing | Test Case Documentation
|  | Make Test Case document of what occured using our system | 4 |  | Kevin | No
Dates: 3/15 - 5/01 | Totals for this Iteration |  | 38 | 0
|  |  |  | Estimated | Actual Hours
|  |  | Planning Iteration | 63 | 76.5
|  |  | Design Iteration | 54 | 53
|  |  | Creation Iteration | 100 | 156
|  |  | Total Estimate Hours | 170
|  |  | Total Actual Hours | 214.5